## Features
Feature | Sub Feature | Priority | Status | Description
Web API | Insert, Delete, Update for TaskLists | 1 | Done
Azure Cloud service | Implement Logging/Diagnostics | 1 | Done
Azure Cloud service | Get the MVC page running in Azure | 1 | Done
WinPhone interface | Details page | 1 | Done
Website interface | initial implementation | 1 | Done
WinPhone interface | Hook up Update and Delete for Tasks to web service | 1 | Done
WinPhone interface | Add, Update, Delete for TaskLists | 1 | Done
WinPhone interface | Update logic for tasks | 1 | Done
WinPhone interface | Details page - type selectors for calendar, loc, etc | 1 | Done
WinPhone interface | "More" details | 1 | Done
WinPhone interface | Configurable details | 1 | Done
Web API | Configuration for details | 1 | Done
Web API | Proper authentication | 2 |  | use real HTTP auth (and ASP.NET auth?)
iPhone interface |  | 2
iPad interface |  | 2
Android interface |  | 2
Task ontology |  | 2
Auction interface |  | 2
Task completer interface |  | 2
WinPhone interface | Test infra for queue | 2
Website interface | Remember the Milk importer | 2
WinPhone interface | Auto-refresh | 2
Amazon Cloud service |  | 3
Win8 interface |  | 3
Outlook add-in |  | 3
WinPhone interface | Live tile for the tasks due today | 3

## Bugs
ID | Bug | Area | Priority | Related | Size | Status | Resolved | Description
1 | HttpWebRequest doesn’t process non-200's | Windows Phone | 3 |  | 5 | Closed | Fixed | All non-200 HttpStatusCodes result in a WebException and no differentiation in status code; switch to HttpClient?
2 | GetCurrentUser returns stale data | Web API | 2 |  |  | Closed | Fixed | EF over-aggressive caching and exogenous changes lead to stale data being returned from GetCurrentUser. Unclear how to fix this.
3 | CreateUser never works | Windows Phone | 1 | 1 | 1 | Closed | Fixed | Until 404 can be processed from the WebAPI, can't create users
4 | Sychronizing tasklists doesn't work | Windows Phone | 2 |  |  | Closed | Fixed | Reimplement feature based on design doc
5 | GetTaskListsForUser never gets invoked | Web API | 1 |  |  | Closed | NoRepro | WebAPI never gets called from WP client even though fiddler works fine
6 | Move URL to config | Windows Phone | 3 |  | 2 | Active |  | URL needs to be in config as opposed to defined as a constant in code. See http://www.wpseven.de/2010/08/app-config-for-wp7-applications/
7 | Enqueue isn't able to read the queue | Windows Phone | 1 |  |  | Closed | Fixed | The queue is getting written to but somehow not getting deserialized correctly
8 | using(isolatedstorage) in requestqueue | Windows Phone | 2 |  |  | Closed | WontFix | Use the static IsolatedStorage
9 | isAuthenticated is false after saving creds | Windows Phone | 2 |  |  | Closed | Fixed | After a successful save, isAuth should be true (and tasklists should be retrieved, and requestqueue flushed)
10 | CreateTask request never makes it to svr | Windows Phone | 1 |  |  | Closed | Fixed | Route is not configured correctly???
11 | Clean up WebServiceHelper for race conditions | Windows Phone | 3 |  | 2 | Closed | NoRepro | Eliminate race conditions in WebServiceHelper (e.g. move isRequestInProgress = true to earlier in the calls)
12 | Remove ID's from the Task Edit page | Windows Phone | 2 |  |  | Closed | Fixed | Add a metadata attribute?
13 | Fix More button on Task Page | Windows Phone | 3 |  |  | Closed | Fixed | IsEnabled is the wrong flag - need to remove the button
14 | Fix queuing algorithm | Windows Phone | 1 | 37 |  | Closed | Fixed | Queuing algo needs to find an entity by new taskID and replace it if it's already in the queue instead of inserting a new one
15 | Fix update requestrecord logic | Windows Phone | 1 |  |  | Closed | Fixed | Fix the Type Name (shows up as List')
16 | Fix Tasks.count | Windows Phone | 2 |  |  | Closed | ByDesign | Tasks.Count isn't accurately showing up (databinding issue?)
17 | TaskListID isn't binding correctly in details page | Windows Phone | 2 |  |  | Closed | Fixed | TaskListID shows up as 0 in the databound control
18 | Add a Completed field to the Task (in all places) | Windows Phone | 1 |  |  | Closed | Fixed | Both Web API and Phone client (don't forget to fix Copy()!)
19 | Refresh TaskList after successful pswd chnge | Windows Phone | 2 |  |  | Closed | Fixed | When new creds are entered into the settings tab, the GetTaskLists isn't called
20 | Task Delete results in exception | Windows Phone | 1 |  |  | Closed | Fixed | Deleting the fifth task in a list of six tasks triggered an exception. MainViewModel:380
21 | User creds disappear from settings dialog | Windows Phone | 1 |  |  | Closed | Fixed | After a crash (or even after a restart) of the app on the phone, the user/pass disappear
22 | Databinding of tasklist in tasklistpage is broken | Windows Phone | 1 |  |  | Closed | Fixed | Doesn't update after a task is created
23 | AutoCompleteBox not autocompleting | Windows Phone | 1 |  |  | Closed | Fixed | Fix autocomplete box
24 | Format phone number properly | Windows Phone | 3 |  | 0.5 | Active
25 | Implement boolean handler for RenderEditTab | Windows Phone | 1 |  |  | Closed | Fixed
26 | Implement list-like (e.g. priority) handler for RenderEditTab | Windows Phone | 1 |  |  | Closed | Fixed | this needs to be implemented as a listpicker (e.g. priority)
27 | Implement multi-add dialog | Windows Phone | 1 |  |  | Closed | Fixed
28 | Need data reduction algorithm for GetUserData | Windows Phone | 3 |  | 8 | Active |  | Only retrieve what's changed…
29 | Avoid triggering UpdateTask when TaskList initializes | Windows Phone | 1 |  |  | Closed | Fixed | When TaskListPage loads, the two-way databinding causes the task's Checked handler to be called, which generates a gratuitous UpdateTask
30 | Implement "Actions" tab for Tasks…. | Windows Phone | 1 |  |  | Closed | Fixed | Actions can map a location, bring up a website, mail a person, call a person…
31 | shrink detail fonts and tasklist fonts | Windows Phone | 1 |  |  | Closed | Fixed | fonts look bad
32 | Implement Delete for Tasklists | Windows Phone | 2 |  |  | Closed | Fixed | implemented but not fully working
33 | Implement local task ID | Windows Phone | 1 | 37 |  | Closed | Fixed | Can't find tasks without a local taskID if they haven't been synced with the server yet…
34 | Switch from passing indexes to passing local taskID's | Windows Phone | 1 | 33 |  | Closed | Fixed | when navigating between pages, pass local tasklistID's and taskID's
35 | Get Constants from server | Windows Phone | 1 |  |  | Closed | Fixed | currently using defaults from client rather than downloading new data from server
36 | Change popup color to Gray | Windows Phone | 3 |  |  | Closed | Fixed
37 | Change all ID's to GUID's | Windows Phone | 1 |  |  | Closed | Fixed | Do this so that the client can generate the GUID's authoritatively instead of relying on the server
38 | Updating TaskList doesn't work | Windows Phone | 1 |  |  | Closed | NoRepro | Unclear what happens
39 | Queue logic for multiple updates doesn't work | Windows Phone | 1 |  |  | Closed | Fixed | Two updates to the same task appear in the queue
40 | User.ID is assigned to junk before the ID is retrieved | Windows Phone | 1 |  |  | Closed | Fixed | This results in new tasklists getting added with a bogus TaskList.UserID
41 | Crash when a tasklist is deleted, then navigated back to | Windows Phone | 1 | 34 |  | Closed | Fixed | GoBack() puts us back in TaskListPage, trying to find the deleted list. Need to GoBack again.
42 | Non-empty tasklist does not delete | Windows Phone | 1 |  |  | Closed | Fixed | Tasklists that have members fail on delete. The remove on the tasks fails. (solution - no need to remove tasks - cascade works automatically)
43 | Find a way to dequeue a failed request | Windows Phone | 3 | 1 | 3 | Active |  | A request should be dequeued if the web service call succeeded and returned a real value (so far this isn't really a problem since CUD ops are forgiving)
44 | Pivots for different sorts | Windows Phone | 1 |  |  | Closed | Fixed | Initial implementation (static, not table-driven)
45 | Colors and captions for Tasks and TaskLists | Windows Phone | 1 |  |  | Closed | Fixed | put meaningful information in the mainpage and tasklist lists
46 | SelectionChanged event gets triggered when sort changes | Windows Phone | 1 |  |  | Closed | Fixed | need to fix the ListBox.SelectionChanged event handler because it is now called spuriously whenever a list changes
47 | When sorting by due, put nulls at the end | Windows Phone | 1 |  |  | Closed | Fixed | currently null due values sort to the beginning of the list
48 | Add about box | Windows Phone | 1 |  |  | Closed | Fixed | add an about box with developer info and feedback link
49 | Add welcome text to main screen | Windows Phone | 1 |  | 0.5 | Closed | Fixed | To get started, add a list using the + icon at the bottom of this page. To sync your data, touch the settings page.
50 | Remove buttons from about tab | Windows Phone | 1 |  |  | Closed | Fixed
51 | Secondary sort on name for due/priority sorts | Windows Phone | 2 |  |  | Closed | Fixed | due and priority should sort by name second. Implemented but not working yet.
52 | Implement tags | Windows Phone | 1 |  |  | Closed | Fixed | Inserting tags at the same time as tasks doesn't seem to work some of the time
53 | Implement tag service | Web API | 1 |  |  | Closed | Fixed
54 | Email tasklists data | Windows Phone | 1 |  |  | Closed | Fixed
55 | Add Offers to data model | Web API | 1 |  | 4 | Active
56 | Add Offers implementation | Windows Phone | 1 | 64 | 4 | Active
57 | Add ability to create custom sorts for list types | Windows Phone | 2 | 25 | 2 | Active
58 | Add "import from template" | Windows Phone | 2 |  |  | Closed | Fixed
59 | Postpone feature | Windows Phone | 2 |  |  | Closed | Fixed | Only offer postpone action for tasks that are overdue (or due today)
60 | Implement tasks page | Windows Phone | 2 |  |  | Closed | Fixed | Add a tasks tab to the mainpage
61 | Implement ListTypeEditor | Windows Phone | 2 |  | 2 | Active |  | not implemented yet
62 | Do tilt effect for selection | Windows Phone | 1 |  |  | Closed | Fixed | not implemented yet
63 | Add splash screen | Windows Phone | 1 |  | 1 | Closed | Fixed
64 | Add ProgressBar when network ops are in effect | Windows Phone | 1 |  |  | Closed | Fixed
65 | Add "connected" icon | Windows Phone | 1 |  |  | Closed | Fixed
66 | Implement listtypes page | Windows Phone | 2 | 25 | 1 | Active |  | Add a listtypes page to the mainpage
67 | Add Location to shopping list type | Windows Phone | 2 |  | 1 | Active
68 | Move About and Settings to menu items | Windows Phone | 2 |  |  | Closed | Fixed
69 | Add List as a Task Type | Windows Phone | 2 |  |  | Closed | Fixed
70 | After PlayQueue need to retrieve all user data | Windows Phone | 2 |  |  | Closed | Fixed | in case the update was for a new listtype or tag…
71 | Add some ability to collect coupons while you're shopping | Windows Phone | 2 |  | 10 | Active
72 | Turn on TaskTags in service | Web API | 1 |  |  | Closed | Fixed
73 | Add search to tasklist pages | Windows Phone | 2 |  |  | Closed | Fixed | added to tasks tab - not anywhere else (for now)
74 | Rollback the queue consolidation code | Windows Phone | 1 |  |  | Closed | Fixed | This is buggy in the case of inserting a task, then updating it by adding a tag (which will cause the update to happen before the tag insert)
75 | Implement display property Tags.TaskCount | Windows Phone | 3 |  | 2 | Active |  | count of tasks in each of the tags (referenced on MainPage.xaml)
76 | Entering creds does not refresh the tasklists | Windows Phone | 1 |  |  | Closed | NoRepro | when first connecting to the service, the tasklists aren't refreshed
77 | Low-pri icon | Windows Phone | 1 |  |  | Closed | Fixed | create low-priority icon
78 | Settings -> default tasklist | Windows Phone | 2 |  |  | Closed | Fixed | create tab for default tasklist
79 | Updating a task by adding a tag to an existing tag doesn't work | Windows Phone | 1 |  |  | Closed | Fixed | Still some work on referential integrity
80 | Add action to navigate to linked list target | Windows Phone | 1 |  |  | Closed | Fixed
81 | Reverse IsComplete and LinkedListID in sort order | Windows Phone | 1 |  |  | Closed | Fixed | makes linked list ID look better
82 | Crash when a tag is selected, then add is clicked | Windows Phone | 1 |  |  | Closed | Fixed
83 | Add "search results" header in tasks tab on mainpage | Windows Phone | 1 |  |  | Closed | Fixed
84 | Add tabstops | Windows Phone | 1 |  |  | Closed | Fixed
85 | Have a bunch of data, connect to a new phone - get extra lists | Windows Phone | 2 |  | 2 | Closed | Fixed | need some way to stop the generation of garbage lists for users that want to reconnect
86 | Add color logic to tags, and display on TaskList | Windows Phone | 2 |  | 2 | Closed | Fixed
87 | Implement recurring tasks | Windows Phone | 2 |  | 5 | Active
88 | Navigation bug: "No Fragment support right now" | Windows Phone | 2 |  | 2 | Closed | Fixed | intermittent bug (only shows up under debugger) - race condition (mainpage->click task->get nav exception)
89 | Invoking the checked handler twice too quickly crashes app | Windows Phone | 1 |  | 2 | Closed | Fixed | issue involves reading and writing to the request queue at the same time (IsolatedStorage exception)
90 | Add map handler for address fields | Windows Phone | 1 |  | 3 | Closed | Fixed | initial implementation
91 | Add linked accounts | Windows Phone | 1 |  | 3 | Active
92 | Implement add to calendar | Windows Phone | 2 |  | 3 | Active
93 | Create tabstops for list editor (and tag editor?) | Windows Phone | 2 |  | 0.25 | Closed | Fixed
94 | Connected icon shouldn't be connected if user not entered | Windows Phone | 1 |  | 0.5 | Closed | Fixed | repro'ed using the emulator
95 | Save in settings is misleading since account wasn't created or synced | Windows Phone | 1 |  | 0.5 | Closed | Fixed | need to figure out what save actually does if the account wasn't created or synced
96 | ConnectedText can go away | Windows Phone | 2 |  | 0.25 | Closed | Fixed | remove connected text from settings page
97 | NoCache header needs to be set for non-success cases | Web API | 1 |  | 0.25 | Closed | Fixed
98 | Get text values from ListEditor and TagEditor | Windows Phone | 2 |  | 0.25 | Closed | Fixed | name values don't get picked up because two-way databinding
99 | Live tile | Windows Phone | 3 |  | 4 | Active
100 | Proper authentication | Windows Phone | 2 |  | 8 | Active |  | use HTTPS and HTTP auth
101 | Auto-sync of user data | Windows Phone | 2 |  | 2 | Active
102 | Clickable connected icon -> settings | Windows Phone | 2 |  | 0.5 | Active |  | click the imagebutton to get to the settings page
103 | Profile the task-check event on tasklistpage | Windows Phone | 2 |  | 1 | Closed | Fixed | checking a task is slow. Put Write to Isolated Storage back into background thread?
104 | Write a script to dump the SQL Azure DB content | Windows Phone | 2 |  | 2 | Active |  | need to script the SQL Azure database
105 | Change "search" to "filter" on mainpage | Windows Phone | 2 |  | 0.25 | Closed | Fixed
106 | Change "To Do" listtype to "To Do List", "Shopping List" | Windows Phone | 2 |  | 0.25 | Closed | Fixed | change both in mainviewmodel.cs and in the database
107 | Add description to text in actions tab | Windows Phone | 2 |  | 0.25 | Closed | Fixed | if Name and Description are set, they should be displayed in Actions page
108 | Due date sometimes gets set to one day earlier | Windows Phone | 1 |  | 2 | Closed | Fixed | change database schema from Date to DateTime OR do some processing on the Due Date before inserting
109 | Create better sort order for tasks pane | Windows Phone | 2 |  | 1 | Closed | Fixed | due, priority, name
110 | WriteTaskLists race results in exception/crash | Windows Phone | 1 |  | 2 | Closed | Fixed | race between write of tasklists from change operation and the write of tasklists that happens when the service returns (fixed by making things synchronous)
111 | Don't show red duedate for completed tasks | Windows Phone | 1 |  | 0.25 | Closed | Fixed
112 | Importing from template will not import tagged items | Windows Phone | 1 |  | 1 | Closed | Fixed | tasktags need to be recreated
113 | Add "lists" button to tasklistpage | Windows Phone | 1 |  | 1 | Closed | Fixed | need lists button to get back to the lists
114 | Tasks collection must include all tasks, but not display in tasks page | Windows Phone | 1 |  | 0.5 | Closed | Fixed | tasks tab needs to filter out the templated tasks even though they exist in the Tasks collection
115 | Change icon for "view lists" appbar button | Windows Phone | 3 |  | 1 | Closed | WontFix | change it to something that indicates lists (as opposed to a folder)
116 | Minimum width for action button | Windows Phone | 2 |  | 0.25 | Closed | Fixed | the buttons are sometimes too thin
117 | More -> more details | Windows Phone | 2 |  | 0.25 | Closed | Fixed | the more button should be renamed to more details, to be consistent with WP calendar
118 | Back button seems to always navigate to Lists | Windows Phone | 3 |  | 1 | Active |  | back button sometimes gets stuck always navigating back to Lists (instead of tags or tasks which were in the back stack)
119 | Change listpicker max value | Windows Phone | 1 |  | 0.5 | Closed | Fixed | listpicker shows ugly fullscreen version beyond a certain number of items
120 | Make priority into listpicker in edit dialog | Website | 1 |  | 2 | Closed | Fixed | currently it's just an integer - not very good
121 | Parse tags in edit dialog | Website | 2 |  | 1 | Active |  | broken
122 | Make linked list ID into listpicker in edit dialog | Website | 2 |  | 1 | Active |  | broken
123 | delete list | Website | 1 |  | 2 | Closed | Fixed | Initial implementation
124 | login / pull tasklists by user | Website | 1 |  | 4 | Closed | Fixed
125 | edit list | Website | 1 |  | 8 | Closed | Fixed | Initial implementation
126 | add list | Website | 1 |  | 1 | Closed | Fixed
127 | edit task needs to refrain from recreating dialog every time | Website | 2 |  | 3 | Closed | Fixed
128 | need to escape some fields (e.g. name) | Website | 1 |  | 1 | Closed | Fixed
129 | honor the "more" categorization for fields | Website | 1 |  | 2 | Closed | Fixed
130 | set the priority value correctly in the task edit dialog | Website | 1 | 127 | 1 | Closed | Fixed
131 | Remove done tasks from Tasks tab | Windows Phone | 2 |  | 0.25 | Closed | Fixed
132 | Way to remove Due date from Windows Phone task page | Windows Phone | 2 |  | 1 | Active
133 | Ability to sort tasks in tasklists | Website | 1 |  | 2 | Closed | Fixed
134 | KeyUp event in add task span gets invoked multiple times | Website | 2 |  | 2 | Active
135 | Sort lists in phone application | Windows Phone | 2 |  | 2 | Active
136 | Edit dialog saves wrong task | Website | 1 |  | 0.5 | Closed | Fixed
137 | Add a refresh tasklists button to the website | Website | 2 |  | 0.5 | Active
138 | Date doesn't refresh | Windows Phone | 1 |  | 1 | Closed | Fixed | Changing a date in the task page, then saving, will not reflect the new date in the TaskList page (databinding?)
139 | Make a real address out of a geo-code | Windows Phone | 2 |  | 3 | Active |  | maybe using a google api? http://groups.google.com/group/Google-Maps-API/web/resources-non-google-geocoders
140 | Reconcile new entities instead of retrieving all tasks | Windows Phone | 2 |  | 3 | Active |  | when making any kind of change, remove the need to refresh the entire tasklist from the server…
141 | Perf of tasklist / CollectionViewSource | Windows Phone | 1 |  | 8 | Closed | Fixed
142 | Speech lateny | Windows Phone | 1 |  | 8 | Active |  | figure out how to reduce speech lateny
143 | IMAP client doesn't run in Azure emulator / Azure? | Web API | 1 |  | 4 | Closed | Fixed | SSL library doesn't connect/handle certs under 64-bit azure(?)
144 | markup bug - the footer overlays the tasklist | Website | 1 |  | 2 | Closed | Fixed | tasklist items can render under the footer; also, the scrollbar misbehaves by scrolling the footer up
145 | Map action doesn't come up | Windows Phone | 1 |  | 0.25 | Closed | Fixed | Change action field from Address to Location in SQL Azure (already done in code and sqlexpress)
146 | change default view for tasklists to DueDate | Windows Phone | 2 |  | 0.5 | Closed | Fixed
147 | Fully debug the deployment process | Web API | 1 |  | 3 | Closed | Fixed | The startup tasks don't work like they should
148 | Non-contiguous date field causes bug in sort | Website | 1 |  | 0.5 | Closed | Fixed | Sort seems to terminate on an empty duedate
149 | more than two seconds of voice blow up speech service | Web API | 1 |  | 4 | Closed | Fixed | Speech service needs a lot of work, including streaming the voice wave
150 | Speech operation in progress bug | Windows Phone | 1 |  | 1 | Active |  | Speech helper prematurely sets speechOperationInProgress to false
151 | separate the completed and incomplete tasks | Website | 1 |  | 1 | Closed | Fixed
152 | Welcome link broken in WP7 | Windows Phone | 1 |  | 0.5 | Closed | Fixed | re-created the method on the Home controller
153 | Paint bugs in WelcomeWP7 page | Windows Phone | 1 |  | 1 | Closed | Fixed | the text doesn't fit (needs to scroll), header looks bad (just like it does on non-IE browsers)
154 | Create timeline feature | Web API | 2 |  | 40 | Active |  | allow user to roll forward and backward in time
155 | Normalize date format to yyyy/mm/dd | Website | 1 |  | 1 | Closed | Fixed | dates entered in through dialog box on website will be stored in US format (as will WP7 dates)
156 | null dates sort below filled dates | Website | 1 |  | 0.5 | Closed | Fixed | should sort to after all non-null dates
157 | Fix about box to reflect new company text | Windows Phone | 1 |  | 0.5 | Closed | Fixed
158 | Lists tab needs to update with number of open items | Windows Phone | 2 |  | 0.5 | Closed | Fixed | need to store number of tasks per list in the tasklists file, as well as update this when a sublist is loaded
159 | Edit a List should go to list edit page, not folder editor | Windows Phone | 1 |  | 1 | Active
160 | Add people and permissions to folder editor | Windows Phone | 1 | 161 | 1 | Active
161 | Add people tab and screen to phone app | Windows Phone | 1 |  | 1 | Active
162 | Add people to data model and Web API | Web API | 1 |  | 2 | Active
163 | Migrate strongly-typed Task fields into FieldValues | Web API | 1 |  | 2 | Closed | Fixed
164 | Finer grained conflict resolution on FieldValues | Web API | 2 |  | 1 | Active |  | need to modify the Update() method in ItemResource.cs to support fine-grained conflict resolution of FieldValues
165 | Remove "QuickAdd" menubar icon and make Add do QA | Windows Phone | 1 |  | 0.5 | Closed | Fixed | collapse quickadd into add
166 | ItemTypes used to populate Values dict need to include users | Windows Phone | 2 |  | 1 | Closed | WontFix | Item.CreateValues only uses ItemTypes that come from Constants, not from UserItemTypes
167 | Reimplement ParseFields in ItemPage | Windows Phone | 2 |  | 1 | Closed | Fixed | The code relies on strongly typed Description, Phone, Website, Email properties.
168 | Set the complete field to false on a new ToDo | Windows Phone | 1 |  | 0.5 | Closed | Fixed | otherwise they have funky looking checkboxes
169 | Fix the null state for the complete checkbox | Windows Phone | 1 |  | 1 | Closed | Fixed | need to make the null be a false
170 | Display a bitmap instead of a checkbox for non-ToDo's | Windows Phone | 1 |  | 1 | Closed | Fixed | If an item doesn't have a complete field, need to display something different
171 | Remove the various convenience fields on Item | Windows Phone | 1 |  | 1 | Closed | WontFix | This is to prevent items from accruing all these properties that they don't need
172 | Remove ID from FieldValue to reduce wire size | Web API | 1 |  | 1 | Closed | WontFix | EF needs the ID as a primary key, and without it, it's hard to figure out new FieldValues vs existing ones
173 | DELETE fails against folder | Web API | 1 |  | 1 | Active |  | It appears that the client sends null for FolderUsers which trips up the service. The client needs to add FolderUsers

## Sheet3
979 | 40 | 305 | 278 | 46 | 293 | 4 | 1006 | 3680 | 273.3696 | 3.6581
1019 | 297 | 583 | 147 | 339 | 220 | 3 | 61 | 295 | 206.7797 | 4.8361
1316 | 83 | 730 | 106 | 559 | 563 | 3 | 31 | 207 | 149.7585 | 6.6774
1399 | 46 | 836 | 234 | 1122 | 187 | 3 | 7 | 104 | 67.3077 | 14.8571
1445 | 152 | 1070 | 107 | 1309 | 228 | 4 | 10006 | 38500 | 259.8961 | 3.8477
1597 | 58 | 1177 | 146 | 1537 | 462 | 4
1655 | 83 | 1323 | 249 | 1999 | 197 | 4
1738 | 150 | 1572 | 110 | 2196 | 221 | 3
1888 | 47 | 1682 | 306 | 2417 | 314 | 3
1935 | 79 | 1988 | 505 | 2731 | 482 | 4
2014 | 150 | 2493 | 105 | 3213 | 295 | 4
2164 | 47 | 2598 | 143 | 3508 | 186 | 2
2211 | 91 | 2741 | 237 | 3694 | 255 | 5
2302 | 131 | 2978 | 109 | 3949 | 428 | 5
2433 | 175 | 3087 | 154 | 4377 | 246 | 5
2608 | 83 | 3241 | 280 | 4623 | 189 | 5
2691 | 47 | 3521 | 120 | 4812 | 333 | 3
2738 | 151 | 3641 | 149 | 5145 | 220 | 3
2889 | 82 | 3790 | 448 | 5365 | 291 | 3
2971 |  | 4238 |  | 5656