## Sheet1
Feature/Workitem | Priority | Milestone | AssignedTo | Size
Move the ConnectTo into a NewUser workflow | 2 | Sprint 2 | Steve | 1
Cleanup of Omri's hacky javascript | 1 | Sprint 2 | Steve | 1
Web UX - Settings - Web UX for setting default folders / lists | 1 | Sprint 3 | Steve | 4
Web UX - Settings - Simple Theming (colors, images) | 2 | Sprint 2 | Steve | 4
FieldValue refactor | 1 | Sprint 2 | Omri, Steve | 4
Split the DB (including 3 different DAC's) | 1 | Alpha | Omri | 4
Automate the Constants deployment into SQL | 2 | Sprint 2 | Steve | 2
Setting up multiple deployments (production, dev1, dev2) | 1 | Sprint 2 | Omri | 4
Get our free bizspark resources set up | 1 | Sprint 2 | Omri | 1
Tickle the worker using a direct activation message that causes a dequeue | 2 | Alpha
Investigate alternative speech service (e.g. speech to worker role, ebing, etc) | 1 | Beta
Consider charging more for better performance (hot queue, latent queue) | 3 | Beta
Deployment Upgrade | 1 | Alpha
Automated Deployment | 1 | Beta
Continuous Deployment | 2 | Beta
Remove old speech code | 2 | Sprint 2 | Omri | 2
Make the workers config-driven | 3 | Beta
Finish the declarative workflow definition language (intent -> holes to fill by activities) | 1 | Sprint 2 | Omri | 8
Define sprint 2 workflow / scenarios, identify activities | 1 | Sprint 2 | Omri, Steve | 2
Implement sprint 2 activities | 1 | Sprint 2 | Omri | 16
Web UX - complete controls for all display types | 1 | Sprint 2 | Steve | 24
Web UX - add a list view to the center pane | 1 | Sprint 2 | Steve | 8
Web UX - add a settings page | 2 | Sprint 2 | Steve | 4
Link to calendar (gmail) | 1 | Sprint 3 | Steve | 40
Web UX - calendar view (day view) | 2 | Sprint 2 | Steve | 16
Reconcile FB / AD contacts with existing contacts (simple heuristic based on name) | 1 | Sprint 2 | Omri | 2
Web UX - reorder and move items between lists and folders | 1 | Sprint 2 | Steve | 8
Phone UX - reorder items | 2 | Sprint 2 | Omri | 4
Phone UX - fix bugs in iphone implementation | 1 | Sprint 2 | Omri | 4
Phone UX - complete winphone migration to iOS model | 1 | Sprint 2 | Omri | 8
Review ItemTypes and Fields | 1 | Sprint 2 | Steve | 2
Fix the Tag feature | 2 | Sprint 3 | Omri | 16
Phone UX - honor ordering of items | 1 | Sprint 2 | Omri | 2
Phone UX - auto-upload trace when hitting unhandled exception | 2 | Sprint 2 | Omri | 2
Phone UX - Create vs Sync | 2 | Sprint 2 | Omri | 4
Web UX - clean up the toolbar | 1 | Sprint 2 | Steve | 4
Web UX - folder and list properties | 1 | Sprint 2 | Steve | 4
Phone UX - folder and list properties | 1 | Sprint 3 | Omri | 2
Phone UX - creating and deleting folders and lists | 1 | Sprint 3 | Omri | 2
Web UX - week, month, year view | 1 | Sprint 3
Naming / Branding | 1 | Sprint 2 | Omri | ?
Color / Logo / Styling | 1 | Sprint 3
Get UX Designer cycles | 1 | Sprint 3
Resolve the Trevor thing | 1 | Sprint 2 | Omri | 1
Figure out whether to work with the daily deal guy (YuBit) | 1 | Sprint 2 | Omri | 2
Set up relationship with eBing (do a demo for Gurdeep / Qi) | 1 | Sprint 2 | Omri | 2
Set up relationship with Tom Casey | 1 | Sprint 2 | Omri | 2
Demo for Mike Abbott | 1 | Sprint 3 | Omri | 1
Corporate website - About, Promo video, product description | 2 | Sprint 3 | Steve | 4
Corporate website - open up access to current video/survey? | 1 | Sprint 2 | Steve | 1
Talk to Tim Cooke about name | 1 | Sprint 2 | Omri | 2
System folder for user settings | 1 | Sprint 2 | Steve | 4
Phone UX - data-driven user settings | 2 | Sprint 3 | Omri | 8
Web UX - move viewstate to system folder | 2 | Sprint 2 | Steve | 4
Login through ACS (support facebook, and username/passwd) | 1 | Sprint 3 | Steve | 24
Refactor UserCredential | 1 | Sprint 3 | Steve | 4
159